## RICs
Type | Cause | Effect | Impact | Likelihood | Importance | Response type | Response | Custodian | Dates
[9 empty] | Identification | Occurrence | Closure
R | Work not done in time | Delay in the development of the project | 60 | 50 | 1 | Watch | Complete the work ASAP and restructure the project planning | Miguel Garcia Hernandez
R | Webpage down due to high traffic of users | Bad functionality of the project | 100 | 20 | 1 | Avoid | Optimise the performance of the website server | Eduardo Midon Alejandro
R | 3D visualization crashing | Bad functionality of the project | 90 | 60 | 2 | Avoid | Changes on the script of the visualization until it is stable | Lier Martinez de Morentin
R | Different reference point for the sea lavel in the data | Sea level not accurate to what was intended with the mesurement | 30 | 20 | 0 | Reduce | Check old entries in the dataset and change he when necessary | Juan Alcantara Dominguez
R | Problems understanding the dataset | Wrong functionality in the visualization | 70 | 30 | 1 | Avoid | Study and understand the data | Juan Alcantara Dominguez
R | Python files not working in the webpage | Webpage not working | 100 | 10 | 1 | Avoid | Check continously whether the files are indeed working | Eduardo Midon Alejandro
R | Conflicts when using the git repository | Delay in the development of the project | 40 | 60 | 1 | Accept | Change to a previous version or get together to solve the conflicts | Miguel Garcia Hernandez
R | Problems within the group | Delay in the development of the project | 70 | 30 | 1 | Accept | Organize a meeting and try and solve all the possible issues between members of the team | Miguel Garcia Hernandez
R | Uncorrect assignment of user permissions | Users would have access to administrator functionalitites | 30 | 10 | 0 | Avoid | Make sure the peemissions are correct and checking woth the administrators if they do have those permissions | Lier Martinez de Morentin
R | Client unsatisfied with the implementation o the requirements | Failed to satisfy the client's need | 70 | 20 | 1 | Avoid | Keep constant contact with the client and ask for feedback when necessary | Miguel Garcia Hernandez
R | Compatibility issues within the different software | Delays and wronkg functionality | 70 | 50 | 2 | Avoid | Study the different software and how to stablish connections between them | Lier Martinez de Morentin
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: One of R = Risk I = Issue C = Change
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Short text to explain the source of the RIC
Note on C1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Short text describing the effect of the RIC
Note on D1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Percentage rating of the impact of the risk on the project where 0 is negligible and 100 is disastrous.
Note on E1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Percentage rating of the likelihood of the risk where 0 is impossible and 100 is certain.
Note on F1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This value is calculated from impact and likelihood and colour-coded.
Note on G1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: One of Accept, Avoid, Mitigate, Transfer, Monitor
Note on H1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Short text describing the action planned (R) or taken (IC)
Note on I1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Name of the person who is responsible for monitoring the RIC until it is closed
Note on J2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Date that the RIC was identified
Note on K2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Date that the RIC occurred
Note on L2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Date that the RIC was closed

## Profile
Impact
High | 5 | 2 | 0
Medium | 0 | 2 | 0
Low | 2 | 0 | 0
| Low | Medium | High | Likelihood

## Help
Help information |  |  | R | Accept
|  |  | I | Avoid
This file is used for recording and controlling risks, issues and changes (RICs) and should be reviewed and updated regularly. These terms are defined below. |  |  | C | Reduce
Transfer
Risk | A hypothetical event that might occur in the future and which would affect the project |  |  | Watch
Issue | An actual event that occurs and which requires some action to be taken
Change | A (potential) modification to the project definition after it has been finalised
Please refer to the notes below which described the contents of the fields on the main sheet.
Field | Required for | Description
Cause | RIC | Short text to explain the source of the RIC
Effect | RIC | Short text describing the effect of the RIC
Impact | R | Percentage rating of the impact of the risk on the project where 0 is negligible and 100 is disastrous.
Liklihood | R | Percentage rating of the likelihood of the risk where 0 is impossible and 100 is certain.
Significance | Calculated | This value is calculated from impact and likelihood and colour-coded
Response type | R | One of Accept, Avoid, Reduce, Transfer, Watch
Response | RIC | Short text describing the action planned (R) or taken (IC)
Custodian | RIC | Name of the person who is responsible for monitoring the RIC until it is closed
Identification | RIC | Date that the RIC was identified
Occurrence | RIC | Date that the RIC occurred
Closure | RIC | Date that the RIC was closed